## Slide 1
Let’s spend the money wisely!
Training session for beneficiaries with projects under implementation within Interreg VI-A Ro-Bg Programme
18th of June 2025 I Ruse
Key aspects regarding implementation

## Slide 2: Relevant documents for Interreg VI- Ro-Bg Programme rules
Financing contract / agreements (subsidy / co-financing);
Annexes of the financing contracts (Approved Application Form; Milestones for activities
Project Implementation Manual (PIM);
Visual Identity Manual;
Partnership Agreements;
National Legislation regarding public procurement (for Romanian private partners special competitive procedure applies
Other EU or national relevant legislation of provisions related with the object of the project’s objectives (regarding eligibility of expenditures, regarding constructions, protection of the environment, equal treatment and non-discrimination, anti-fraud measures, protection of personal information).

## Slide 3: Project Implementation
Work plan
Implementation of the activities according with the schedule defined in the approved application form
Milestones
Reaching the targets set in Annex 5 (subsidy)
Indicators
Meeting the targets set for each WP
Results
End of implementation or one year after
Five years after implementation
Sustainability
Cooperation
Risk management
Partner reporting
Project reporting
Project communication

## Slide 4: Project Implementation
Project when planning
Project during implementation
Encourage:
Team meetings (kick-off and intermediary),
Clear and constant exchange of information,
Commitment towards reporting,
Joint Steering Committee meetings and decisions.

## Slide 5: Schedule of the activities:
Observe the start date.
Starting the activities earlier than plan is possible, if the intervention logic is not affected, without notification of the project.
Any delay shall be followed by corrective measures for recovery of the delays
Failure to start the activities may result in major risks for project general delays, failure of meeting the targets and decommitment of the budget or financial correction

## Slide 6: Milestones:
Related with both activities and indicators,
Mandatory to be observed,
If not observed, Programme will set corrective measures,
If the corrective measures are not implemented risk for decommitment of the budget.

## Slide 7: Decommitment:
Financial targets are reached for mid implementation period for each partner,
Targets are set in the subsidy contract and cannot be modified,
Expenditure shall be realized and requested for NC verification until the mid implementation,
Shall be included in a partner report,
In half of the implementation falls within of a 4 months reporting period, the partners in risk may submit reports before the deadline. JS will create an exceptional project reporting deadline.

## Slide 8: Contract modifications:
Not recommended, but sometimes necessary;
Flexibility for budget modifications, only applied to real costs, in two scenarios:
1. Reallocation of budget within the categories of expenditures External expertise and services costs, Equipment costs, Costs for infrastructure and works and Staff costs (for projects reporting staff costs as real costs) if:
minimum requirements for technical characteristics are respected according to approved application form (when launching the procurement);
the number of equipment/description of necessary services/works from the description of activities is observed and correlation with activities is clear for all costs.
budget chapter is not exceeded (even the final unit price for different items may vary compared to the amount used for justifying the budget during assessment phase).
the national and European legislation as well as the other Programme rules on procurement are observed. No notification is needed!

## Slide 9: Contract modifications:
2. Reallocation between the budget line of the partner’s budget, up to 10% of the total partner budget. Following restrictions apply:
Can be used when planed activities cost more than originally expected and cannot be used to change the outputs and deliverables;
Only apply to real costs.
Unplanned costs under the partner budget real costs can only be eligible for funding in exceptional cases and must be approved by the Programme
Partner flat rates cannot be changed.
Allowed only once during the project implementation.
Notification is needed!

## Slide 10: Contract modifications:
Minor modifications (Notifications):
Contact data change of the LP or of the project partners.
Change of the euro bank account of the LP and / or National currency bank account(s) of the partners.
Modification of the name of the partner, without changing the identification number of the institution (BULSTAT, fiscal registration number).
Material errors in the text of the contract.
Budget changes between budget lines, up to 10% of the total partner budget.
Minor modifications of the work plan (not affecting the intervention logic).
Other non-substantial changes.

## Slide 11: Contract modifications:
Major modifications (Addendum!):
Changes in the partnership (partner withdrawal – replacement of partner / other partners fully or partially taking over; legal succession; );
Substantial changes in the content of the project.
Changes in the budget (other than flexibility);
Changes between budget lines higher than 10%;
Reallocation of funds between partners
Changes of technical specifications of equipment and services*;
Extension of the implementation period (exceptional cases/max 3 months*).
Other substantial changes.

## Slide 12: Contract modifications:
Technical modifications for constructions:
Mandatory to submit the technical project to JS + legal representative's statement regarding modifications (10 working days since receipt);
All changes shall be presented:
Modification of the emplacement / location of investment;
Modifications of the functionality of the designed spaces / rooms;
Modification of the functional / technological / constructive solutions*;
Modification of the technical – economic indicators of the investment;
Modification regarding the measurements of the investments.
Other substantial changes.
JS will provide feedback on the TP and inform you if addendum is needed!

## Slide 13: Anti fraud policy:
Project Implementation Manual: Measures set out in order to eliminate - fraud risks in public procurement
Strictly follow national procurement rules (Romanian partners have special Programme procedure for procurement;
Never split contracts or manipulate values to avoid legal thresholds.
All personnel involved in procurement must sign and register declarations of no conflict of interest; these must be available for Programme checks.
Apply the “four eyes principle” (double-checking) for all procurement documents.
Ensure transparency, equal treatment, and fair competition in all procurement activities.
Avoid bid rigging, kickbacks, and deliberate mismanagement; use qualified experts for evaluations.
For public partners: use the PREVENT system in Romania where required, and follow all national/EU legal provisions.

## Slide 14: Anti fraud policy:
Project Implementation Manual - Practical guide on fraud
Maintain ethical conduct in all project activities; personal interests must not interfere.
Recommended: Have an internal code of conduct and conflict of interest policy, and ensure all staff are informed. All PTM members shall sign declarations for lack of conflict of interest.
Any situation of conflict of interest shall immediately be addressed and the person in conflict shall be replaced
Pay special attention to procurement, as it is highly susceptible to fraud.
All documents submitted for verification must be genuine; forged documents may have financial consequences for the project.
Use internal audit units to review procurement processes, if available (recommended)
Any suspicion of fraud must be reported to the Programme’s whistleblower contacts (sesizari.proiecte@mdrap.ro for Romania and D.Petkova@mrrb.government.bg, Rositsa.Draganova@mrrb.government.bg, Yana.Koleva@mrrb.government.bg for Bulgaria.

## Slide 15: Tips and best practices:
Carefully read the approved application form before proceeding to implementation of each project activity;
Read the output and result indicators and think even since the beginning what shall be the achievement and how this achievement will be supported by relevant evidence in front of the Programme;
Ensure that each activity is carefully documented from the preparation stage until the end of the implementation
    - for example: for events, project meetings, etc, shall be prepared invitations, agenda, minutes of the meetings / events, pictures, etc).;
    - for services ask the providers to send you reports regarding the performance of their activities, pictures, other relevant documents;
    - for equipment keep track of their distribution within your organization. Take measures to ensure that the purchased equipment is put into operation (not stored in a box and not used, for example)

## Slide 16: Tips and best practices:
Carefully plan your activities. Strictly observe the schedule of the activities and Annex 5 related to the milestones. If delays appear, immediately implement measures for recovery of delays;
For construction public procurement contracts make sure to use the technical documentation submitted together with the approved applications. Differences may be difficult to be done after you already sing the work execution contract;
Appoint a technical responsible for each construction contract and carefully supervise the works and graphic of execution. Ask the construction supervisor (diriginte de santier) to provide regular reports regarding the progress of the works.
Inform the Programme regarding any issue delaying the execution of works.
Don’t accept modification of the execution contract, unless necessary and only after you review all procurement rules and provisions of the work execution contract

## Slide 17: Tips and best practices:
Don’t forget to include provisions regarding the verifications and test related with the executed works;
For renovation of existing buildings, in the earliest stage, an identification of the possible presence of bats and birds as well as the presence of their shelters and nests will be identified, in line with the legal provisions. The activities will be carried out by certified experts (Register of certified experts for the elaboration of environmental studies - Types of studies: Monitoring of biodiversity "MB”);

## Slide 18: Thank you for attention!